# Wakeel v1.0 — Developer Quote

Fixed-price proposal in support of Developer SOW v2.0

| Engagement window | May 22 – May 30, 2026 (5 effective build days; Eid break May 26–29) |
| --- | --- |
| Reference documents | Wakeel Developer SOW v2.0; Wakeel PRD v3.0 |
| Delivery model | AI-assisted solo build (Claude as technical sounding board per SOW §9; AI coding tools for execution) |
| Fixed price | $1,300 USD |
| Not-to-exceed (NTE) cap | $1,500 USD |
| Invoice currency | USD (all milestone payments invoiced and paid in United States dollars) |

# Commercial terms

This quote is a fixed-price engagement of $1,300 USD for all deliverables in SOW v2 Section 2 and PRD v3 Sections 5–10 and 17, subject to assumptions and exclusions below.

The fixed price is not calculated as 59 hours × $20/hour ($1,180). The packaged rate includes integration contingency and fixed-price delivery risk. Hours in the milestone table are indicative only for planning and traceability to SOW §4.

If additional in-scope effort is required beyond the fixed price, work may be billed at $20/hour only until cumulative invoicing reaches the not-to-exceed cap of $1,500 USD (maximum additional exposure: $200 USD). No charges beyond $1,500 without a written change order.

Payment currency: All invoices and payments under this engagement are in USD. SOW §10 references AED; both parties agree USD settlement for this engagement. Payment via bank transfer or other mutually agreed method within 7 days of each milestone.

## Milestone payment schedule (per SOW §10)

| Milestone | % | Amount (USD) |
| --- | --- | --- |
| SOW signature | 30% | $390 |
| Day 4 milestone (May 25) per SOW §4 | 30% | $390 |
| May 30 acceptance per SOW §5 | 40% | $520 |

Payment within 7 days of each milestone. Intellectual property, NDA, and other commercial terms per SOW v2 Sections 10 and 12.

# Indicative hours by milestone (59 hours total)

The following 59 hours align with the SOW §4 calendar. Billing remains fixed-price per Commercial terms above.

| Day | Date | Scope | Hours |
| --- | --- | --- | --- |
| 1 | Thu May 22 | Repo scaffold; GitLab→GitHub mirror live (Day 1); app/llm.py (SOW §6); LangGraph hello-world; Streamlit UI shell with mode toggle; initial Dockerfile | 8 |
| 2 | Fri May 23 | Corpus ingestion (4 UAE statutes); ChromaDB embedding; Interviewer (EN+AR, RTL); Debaters A & B; Loop 1 | 10 |
| 3 | Sat May 24 | Architect + Builder + Validator; Loops 2 & 3; full build-mode via POST /run and UI; audit trail sidebar | 10 |
| 4 | Sun May 25 | Reviewer + Citation Verifier; Loop 4; NDA review copilot template | 10 |
| — | May 26–29 | Eid — light cleanup buffer | 4 |
| 5 | Fri May 30 | Counter-Proposal Drafter + Synthesis; Loop 5; UI polish; 6+6 examples; pinned requirements.txt; sample logs (all 5 loops); docs; Docker; 3 walkthrough videos | 12 |
| — | Ongoing | 4× daily check-ins (May 22–25) | 1 |
| — | May 31+ | Acceptance review bug fixes (SOW §5) | 4 |
|  |  | Indicative total | 59 |

# In scope (summary)

10 agents orchestrated via LangGraph with 5 feedback loops logged to JSONL

POST /run on port 8000 (build and use modes)

Shared LLM client wrapper per SOW §6 (app/llm.py)

ChromaDB corpus: 4 UAE Federal statutes with generic ingestion pipeline

Arabic intake in build mode (Interviewer); English downstream

≥3 Arabic test inputs in input_examples/build_mode/ with corresponding outputs (SOW §2 Arabic intake); plus ≥1 Arabic build-mode example in the 6 total input examples (SOW §2 Documentation). If founder prefers a single Arabic example set, SOW must be amended in writing before Day 1.

Streamlit chat UI on port 8001 with mode toggle, audit sidebar, RTL input

NDA review copilot template end-to-end

GitLab as source of truth; GitLab→GitHub auto-mirror live from Day 1

Docker (ports 8000 and 8001); requirements.txt with pinned versions; .env.example

Sample run logs in logs/ demonstrating all 5 feedback loops

README.md, docs/architecture.md, input/output examples

3 technical walkthrough videos in demos/

# Out of scope

Per SOW v2 Section 3, including: Arabic output, auth/multi-tenancy, DIFC/ADGM, polished judge-facing demo video, metadata.json/submission portal, production observability, hosting beyond local Docker.

# Assumptions

Founder provides LLM credentials, statute source files, sample NDAs, and Arabic test inputs by Day 1 (SOW §9).

Jais fallback to standard reasoning model if unavailable Day 1 — no rebuild penalty (SOW §2).

Claude available daily for prompt engineering, agent design review, and unblocking.

AI-assisted coding tools used throughout; without AI support, timeline and price would require renegotiation.

May 31 acceptance review covers bug fixes against SOW §5 criteria only, not new scope.

LLM/API usage costs are founder-provided and not included in this quote.

NTE cap ($1,500 USD) applies only to in-scope work; material additions require a written change order.

# Risks and flags (SOW §11)

Five working days for full v1.0 delivery is tight; statute files, credentials, and GitLab access must be ready Day 1.

SOW §6 LLM wrapper requirements are non-negotiable and quoted to spec.

NTE cap ($1,500 USD) covers reasonable slip on Loops 4–5, integration, and May 31 fixes; not new features.

May 24 EOD (SOW §4): if Days 1–3 milestones are not met, founder + Claude and developer meet to assess scope cuts per PRD cut sequence.

May 28 mid-Eid (SOW §4): optional 30-minute call to confirm May 30 delivery is on track.

# Developer responses (SOW §11)

Stack comfort: Comfortable with LangGraph, FastAPI, ChromaDB, Streamlit, Docker, OpenAI-SDK-style clients. Weaker area: Arabic RTL edge cases in Streamlit (addressable with detection and styling).

Arabic: Will deliver per SOW §2: ≥3 Arabic inputs in input_examples/build_mode/ unless founder agrees in writing to amend SOW to ≥1 before build start.

Availability: Substantial full-time commitment May 22–25 and May 30; no work expected May 26–29 (Eid).

Timeline: May 30 deadline feasible with Day 1 readiness, daily check-ins, and scope-cut sequence per PRD if needed.

Quote: Fixed price $1,300 USD; not-to-exceed $1,500 USD. All invoices in USD.

# Sign-off

Upon signature, this quote is incorporated into the commercial terms of Developer SOW v2.0.

Founder: _____________________________    Date: _______________

Developer: ___________________________    Date: _______________